## JLC Backlog Status
# | Section | Priority | Item | Owner(s) | Status | Evidence / Notes
1 | Content rules | P0 | Each Practice game = exactly 3 questions | Dev / Content | Done | kLessonPracticeQuestions=3 (lesson_practice_config.dart:4); wired via sessionRounds in hiragana_lesson1_screen.dart:588 & n5_lesson_video_screens.dart:46
2 | Content rules | P0 | No hiragana anywhere in Lesson 1 (Bengali + romaji only) | Content / Dev | QA / Review | Cannot confirm by code; needs content pass through every Lesson 1 screen/card/question
3 | Content rules | P0 | Remove the "শুনুন" (listen) audio prompt from Lesson 1 | Dev | To-do | Still present: 'সব শুনুন' / 'ভুলগুলি শুনুন' (n5_hero_number1_lesson_screen.dart:4476)
4 | N5 landing | P0 | Show Lesson 1 outline — full topic list | Dev | Done | Lists all lessons + kana section (course_list_screen.dart:934)
5 | N5 landing | P0 | Only first 3 topics accessible; lock the rest | Dev | To-do | No lock logic; all lessons tappable (course_list_screen.dart:934)
6 | N5 landing | P0 | Each topic = thumbnail video, vertical scroll | Dev / Design | Partial | Vertical scroll done; tiles are text + play icon, not video thumbnails
7 | N5 landing | P0 | Hide Lessons 2, 3, … for now | Dev | To-do | All 7 lessons shown
8 | JLC structure | P1 | JLC = 4 cards (Language · Culture · Career · Wisdom) | Dev / Design | Done | jlc_home_screen.dart:177; Culture/Career/Wisdom -> coming-soon
9 | JLC structure | P1 | Language page layout (video -> level scroll -> Practice/Challenge) | Dev | Done | jlc_language_screen.dart:100; Japan video is a coming-soon placeholder, not a real video
10 | হিরো নাম্বার ১ landing | P1 | Page layout (top video; below R/W/L/S -> practice grid; mid score bar; bottom Challenge -> সাজাও) | Dev | Partial | Video + practice grid + সাজাও present (hiragana_lesson1_screen.dart:433); MISSING horizontal score bar + Reading/Writing/Listening/Speaking labels
11 | হিরো নাম্বার ১ landing | P1 | Keep "বলতে পারো"; omit Match Master | Dev | Partial | Both still in games list (n5_hero_number1_lesson_screen.dart:234); Match Master not surfaced on landing but not removed
12 | Practice UI/UX | P1 | Relaxed, vibrant UI (emoji + vibrant cards; calming motion) | Design / Dev | Partial | Vibrant gradient cards done (lesson_practice_game_cards.dart:175); MISSING emoji titles + wave/water/ripple/flower motion
13 | Practice UI/UX | P1 | Remove the progress bar | Dev | Partial | Removed in hero game; STILL present in Greetings (n5_hi_hello_lesson_screen.dart:491, 1382, 1668)
14 | Practice UI/UX | P1 | Remove the second line from the top | Dev | To-do | Confirm location and remove
15 | Practice UI/UX | P1 | Replace text labels with icon buttons (underline grid, selected highlighted) | Dev / Design | To-do | Current cards are icon + text, not underline-style icon buttons
16 | Practice UI/UX | P1 | Completion state on icons (blue tick done; underline while inside) | Dev | To-do | No completion-tick logic
17 | Practice UI/UX | P1 | Add scroll arrow to the practice bar | Dev | To-do | Not present
18 | Greetings (Part 2) | P1 | Practice + Challenge = phrase match | Dev / Content | Done | ফ্রেজ ম্যাচ (n5_lesson_video_screens.dart:171)
19 | Greetings (Part 2) | P1 | こんにちは card design (speaker = yellow circle + blue speaker; larger meaning font) | Design / Dev | Partial | konnichiwa + romaji + speaker + 'বাংলা অর্থ কী?' present (n5_hi_hello_lesson_screen.dart:2206); verify exact styling
20 | Greetings (Part 2) | P1 | Option cards: time-of-day image on right (🌅☀️🌇🌙) | Design / Content | Partial | Uses wb_sunny / wb_twilight icons (n5_hi_hello_lesson_screen.dart:166); MISSING full morning/noon/evening/night image set
21 | Answer feedback | P1 | Wrong: reduce shake; yellow card-border only; Doyo (Pengu) popup hands crossed | Dev / Design | To-do | Shake exists; no Pengu popup in lesson game screens; border-only highlight unverified
22 | Answer feedback | P1 | Right: blue Doyo (Pengu) popup with thumbs up | Dev / Design | To-do | No Pengu popup in lesson game screens
23 | Answer feedback | P1 | Option text alignment -> center-right | Dev | To-do | Needs review
24 | পড়ে বলো | P1 | Shorten the question text | Content | To-do | Scene strings are long (n5_hi_hello_lesson_screen.dart:231)
25 | পড়ে বলো | P1 | Omit the trick-question briefcase icon | Dev | To-do | business_center_rounded still present (n5_hi_hello_lesson_screen.dart:232)
26 | পড়ে বলো | P1 | Preserve the trick logic (office context = wrong こんにちは) | Content | Done | office -> Ohayo gozaimasu (n5_hi_hello_lesson_screen.dart:231)
27 | Challenge & leaderboard | P2 | Module Challenge: continuous mixed, faster = more points, leaderboard | Dev | Partial | Speed Boss + scoring/timer exist; no leaderboard wired into module challenge
28 | Challenge & leaderboard | P2 | সাজাও Challenge is timed (lowest time -> record + leaderboard) | Dev | Partial | Stopwatch + 'সময়:' display exist (n5_hero_number1_lesson_screen.dart:1257); MISSING record + leaderboard save
29 | Challenge & leaderboard | P2 | সাজাও audio (wire chosen voice) | Dev | To-do | Blocked by voice-options decision
30 | Decisions | P0 | Font & colour scheme for Q&A (yellow-on-black Q / blue-on-yellow A) | Decision / Content / Design | Decision | Needs final call + legibility check for Bengali + romaji
31 | Decisions | P0 | সাজাও voice options — talents, TTS presets, or difficulty modes? | Decision | Decision | Blocks সাজাও audio ticket
32 | QA pass (N4 tester) | QA | Content rule: zero hiragana in Lesson 1; all Bengali + romaji | Tester | QA / Review
33 | QA pass (N4 tester) | QA | Romaji accuracy across every card | Tester | QA / Review
34 | QA pass (N4 tester) | QA | Bengali translation accuracy | Tester | QA / Review
35 | QA pass (N4 tester) | QA | Greeting -> time-of-day image mapping correct | Tester | QA / Review
36 | QA pass (N4 tester) | QA | পড়ে বলো office-context trick behaves as intended | Tester | QA / Review
37 | QA pass (N4 tester) | QA | Feedback states correct on every game | Tester | QA / Review
38 | QA pass (N4 tester) | QA | Completion ticks appear after each game | Tester | QA / Review
39 | QA pass (N4 tester) | QA | 3-question rule holds on every Practice game | Tester | QA / Review
40 | QA pass (N4 tester) | QA | Access logic: only first 3 topics open; Lessons 2–3 hidden | Tester | QA / Review

## Summary
EZ Trainz — JLC Backlog Status Summary
Status | Count | Meaning
Done | 6 | Built and verified in code
Partial | 9 | Started; needs finishing
To-do | 13 | Not started
Decision | 2 | Needs a call before build
QA / Review | 10 | Pending content/QA pass
Total | 40